## Sumary
iMX6 Rex Development Baseboard Time Development statistics
http://www.imx6rex.com/
Duration |  | Description
Hours | Minutes
74 | 58 | SCHEMATIC
35 | 52 | Creating schematic
5 | 31 | Preliminary schematic checking before placement
3 | 35 | Creating block diagram
25 | 7 | Schematic checking
1 | 1 | Fixing schematic errors & warnings
3 | 0 | Updating schematic from RF checking
0 | 52 | Variants
48 | 46 | LIBRARIES
2 | 21 | Creating components copied from reference schematic
16 | 58 | Creating footprints
4 | 7 | Schematic library checking
6 | 52 | Footprint checking
2 | 25 | Creating purchasing BOM
5 | 37 | Finding mating connectors
10 | 26 | Checking arrived order, checking footprints
147 | 13 | PCB
27 | 41 | Component placement
13 | 48 | Preliminary layout
0 | 41 | Preliminary power connection
19 | 38 | Connecting local connections, components reconnection
14 | 44 | First optimization
3 | 8 | Updating PCB & footprint from RF checking
14 | 19 | Second optimization
5 | 37 | Layout checking
17 | 47 | Length matching
10 | 15 | Final optimization (no diff. pairs)
5 | 22 | Creating power planes
1 | 15 | Working on assembly layers
12 | 58 | Creating mechanical layers & Generating output documents
270h | 57min | Total

## Total
Total: 270.95 hours

## Schematic
Total: 74.97 hours

## Libraries
Total: 48.77 hours

## PCB
Total: 147.22 hours

## Sheet1
iMX6 Rex Development Baseboard Time Development statistics
http://www.imx6rex.com/
Name of task | Duration
| Hours | Minutes |  |  |  |  | time in hours |  |  | percentage
SCHEMATIC |  |  | Summary
Creating schematic | 35 | 52
Preliminary schematic checking before placement | 5 | 31 | All together | 270 | 57 |  | 270.95
Creating block diagram | 3 | 35
Schematic checking | 25 | 7 | Schematic (74.97h) | 74 | 58 |  | 74.9667 |  | 27.6681
Fixing schematic errors & warnings | 1 | 1 | Schematic drawing (44.33h) | 44 | 20 |  | 44.3333 |  |  |  | 59.1374
Updating schematic from RF checking | 3 | 0 | Schematic checking (30.63h) | 30 | 38 |  | 30.6333 |  |  |  | 40.8626
Variants | 0 | 52
|  |  | Libraries (48.77h) | 48 | 46 |  | 48.7667 |  | 17.9984
LIBRARIES |  |  | Libraries creating (27.35h) | 27 | 21 |  | 27.35 |  |  |  | 56.0834
Creating components copied from reference schematic | 2 | 21 | Libraries checking (21.25h) | 21 | 25 |  | 21.4167 |  |  |  | 43.9166
Creating footprints | 16 | 58
Schematic library checking | 4 | 7 | PCB (147.22h) | 147 | 13 |  | 147.2167 |  | 54.3335
Footprint checking | 6 | 52 | Placement (27.68h) | 27 | 41 |  | 27.6833 |  |  |  | 18.8045
Creating purchasing BOM | 2 | 25 | Connecting Nets (37.25h) | 37 | 15 |  | 37.25 |  |  |  | 25.3028
Finding mating connectors | 5 | 37 | Improving, Length matching (68.07h) | 68 | 4 |  | 68.0667 |  |  |  | 46.2357
Checking arrived order, checking footprints | 10 | 26 | Finishing (14.22h) | 14 | 13 |  | 14.2167 |  |  |  | 9.657
PCB
Component placement | 27 | 41
Preliminary layout | 13 | 48
Preliminary power connection | 0 | 41
Connecting local connections, components reconnection | 19 | 38
First optimization | 14 | 44
Updating PCB & footprint from RF checking | 3 | 8
Second optimization | 14 | 19 |  | sum of times |  | sholud be equal to |  | and also to
Layout checking | 5 | 37 |  | 270 |  | 270 |  | 270
Length matching | 17 | 47 |  | 57 |  | 57 |  | 57
Final optimization (no diff. pairs) | 10 | 15
Creating power planes | 5 | 22
Working on assembly layers | 1 | 15
Creating mechanical layers & Generating output documents | 12 | 58